## Q4
Week | Backend | Frontend | Ops
2021-10-01 |  |  | Bootstrap Dev Environments
2021-10-08 | Prepare Dataset | User Interface Template
2021-10-15
2021-10-22 | Trained the models | Template Integration
2021-10-29
2021-11-05 | Python Flask App | Forms Implementation
2021-11-12 | Test Continuous Delivery | Test Continuous Delivery
2021-11-19 |  | Connects to an API
2021-11-26
2021-12-03 | Backend ready for QA | Frontend Ready for QA
2021-12-10
2021-12-17 | Backend ready for Prod | Frontend Ready for Prod
| Goals | Goals | Goals
| ML API | Deployed on Azure | Consistent Environments
| Observability | React